# Lead Generation to Predictive Intelligence Platform Plan

# Master Strategy

You are building a Vertical Predictive Lead Intelligence Platform that predicts demand, scores leads, and monetizes outcomes.

# Phase 1: Cash Flow Engine (Days 1–14)

Pick one niche (basement flooding recommended). Build landing page, Facebook groups, close 2–3 contractors, run ads.
Target: $5K–$15K revenue.

# Phase 2: Data Moat (Days 15–45)

Build risk scoring engine, scrape data (weather, permits), automate workflows, track conversions.

# Phase 3: Scale (Months 2–4)

Expand geography, add second vertical, build contractor network, systematize VA roles.
Target: $20K–$60K/month.

# Phase 4: Platform Build (Months 3–6)

Convert system into SaaS (React, Express, PostgreSQL). Add dashboards, CRM integrations, AI scoring.

# Phase 5: Defensible Platform (6–12 Months)

Add predictive intelligence, white-label, expand into industrial energy and CNC verticals.
Target: $50K–$200K/month.

# Capital Allocation ($10K)

Landing pages/tools: $500
Ads: $1,500
VAs: $3,000
Automation: $1,000
CRM/tools: $500
Buffer: $3,500

# Key Insight

Do not sell leads—sell certainty.